## Sheet1
Category | Stories | Estimated Hours | assigned to
User Authentication | departement library staff login pagedesign | 2 | akash
Dashboard | dashboard page design | 3 | sammera
| Dynamic user control effect | 1.5 | akash
| addding sliddig panel effect to dashboard buttons | 2 | akash
| designing add student appform | 2 | kunal
| creating an instance of add student app form in appbody | 1 | kannapa
| designing add book appform | 2 | akarsh
| creating an instance of add book app form in appbody | 1 | akarsh
| designing transcation app form | 2 | gowthan
| creating an instance of transcation app form in appbody | 1 | gowtham
backend design | creating tables in a sqllite database | 2 | akash
| Creating stored procedures | 2 | akash
| linking backend with frontend | 1 | akash
add student | every student details of the departement should be added to borrower table | 3 | sammera
| search student button design | 3 | kannapa
| search student button programming | 1 | kunal
add books | should add every book in a library and when new book arrives it should be added to database | 3 | sammera
| delete book button programming | 3 | kunal
| delete book button design | 3 | akarsh
| Search book button design | 1 | gowtham
| Search book button programming | 3 | kannapa
Transcations | issue book button design | 1 | gowtham
| isuue book button programming | 3 | akash
| return book button design | 1 | sammera
| return book button programming | 1 | akash
about | about app form design | 1 | sammera
| designing in ms word | 0.5 | gowtham
total=50
sprint1
Category | Stories | Estimated Hours | assigned to
User Authentication | departement library staff login pagedesign | 1 | akash
Dashboard | dashboard page design | 3 | sammera
| Dynamic user control effect | 1 | akash
| addding sliddig panel effect to dashboard buttons | 3 | akash
| designing add student appform | 2 | kunal
| creating an instance of add student app form in appbody | 1 | kannapa
| designing add book appform | 2 | akarsh
| creating an instance of add book app form in appbody | 2 | akarsh
| designing transcation app form | 1 | gowthan
| creating an instance of transcation app form in appbody | 1 | gowtham
total = 17
Sprint 2
Category | Stories | Estimated Hours | assigned to
backend design | creating tables in a sqllite database | 2 | akash
| Creating stored procedures | 3 | akash
| linking backend with frontend | 1 | akash
add student | every student details of the departement should be added to borrower table | 2 | sammera
| search student button design | 3 | kannapa
| search student button programming | 1 | kunal
total=12 hour
sprint 3
Category | Stories | Estimated Hours | assigned to
add books | should add every book in a library and when new book arrives it should be added to database | 4 | sammera
| delete book button programming | 3 | kunal
| delete book button design | 2 | akarsh
| Search book button design | 1 | gowtham
| Search book button programming | 2 | kannapa
total =12hour
sprint 4
Category | Stories | Estimated Hours | assigned to
Transcations | issue book button design | 2.5 | gowtham
| isuue book button programming | 3 | akash
| return book button design | 3 | sammera
| return book button programming | 1 | akash
about | about app form design | 1 | sammera
| designing in ms word | 0.5 | gowtham
total=11