## Sheet1
Sprint 1
Category | Story | Time taken | Status
User Authentication | departement library staff login pagedesign | 3 | completed
Dashboard | dashboard page design | 2.5 | completed
| addding sliddig panel effect to dashboard buttons | 2 | completed
| designing add student appform | 3 | completed
| designing add book appform | 2 | completed
sprint 3
Category | Story | Time Taken | Status
add books | delete book button design | 3.5 | completed
| Search book button design | 3 | completed
transcations | issue book button design | 3 | completed
| return book button design | 3 | completed
about | about app form design | 2 | completed
total=16.5
Sprint 2
Category | Story | Time Taken | Status
Dashboard | designing transcation app form | 3 | completed
backend design | creating tables in a sqllite database | 2 | completed
| linking backend with frontend | 1 | completed
add student | every student details of the departement should be added to borrower table | 2 | completed
| search student button design | 1.5 | completed
add books | should add every book in a library and when new book arrives it should be added to database | 2.5 | completed
toatl=12 hour